# Beta Readiness Report

Mero Jugx — what to ship, what to fix, what to defer

| Field | Value |
| --- | --- |
| Document | Beta Readiness Report (v1.0) |
| Verdict | Ready for closed beta after the 11 must-do items in Section 4 are addressed. |
| Estimated work to public beta | 6–9 weeks of focused execution on the gaps below. |
| Audience | Founders, Engineering leadership, Investors |
| Method | Deep code audit + cross-check against README claims + per-module status assessment |
| Code basis | Repository state — April 2026 |

## TL;DR

Mero Jugx has a solid foundation: auth, multi-tenancy, RBAC, payments, observability, and the four flagship apps (CRM, Inventory, Accounting, Board) are production-grade. CMS is feature-complete; HR and Khata are feature-complete-but-beta. Social, Tickets, and Chat are functional scaffolds that need closing-the-loop work.

The honest blockers to a public beta are six in number and well-understood: payment-webhook signature verification across every gateway, Postgres row-level security as a defence-in-depth backstop, automated backups with restore drills, the system-admin dashboard build-out, finishing or hiding Tickets/Chat/Social, and lifting test coverage on the frontend. None of these is research — all are scoped engineering tasks.

The recommended path: close the must-do list, run a 4–6 week closed beta with 25 hand-picked customers, then promote to public beta. Sections 3–7 below give the per-module verdict, the must-do list with effort estimates, the risk register, and the suggested 9-week sequence.

# 1. Per-module status matrix

Verdict legend: Production = ready for general availability. Improvement = solid core, missing edges. Beta = feature-complete but unproven at scale. Stub = scaffold only.

| Module | Verdict | What’s done | What needs to happen before beta |
| --- | --- | --- | --- |
| Mero CRM | Production | Leads, deals, pipeline, clients, contacts, activities, quotes, invoices, payments, automation. 22 frontend pages. e2e tests cover core flows. | Add usability test with a real sales team. Validate quote-to-cash hand-off into Accounting under load. |
| Mero Inventory | Production | Products, warehouses, stock movements, POs, GRNs, sales orders, shipments, requisitions, backorders, valuation reports. 19 frontend pages. | Stress-test stock_movements append rate; add composite index (organization_id, product_id, created_at). |
| Mero Accounting | Production | 22 entities. COA seeded for Nepal. JEs, customer/vendor invoices, banking, fixed assets, budgets, multi-currency, year-end closing. 14 pages. | Run a real fiscal-year close in a sandbox tenant end-to-end. Audit JE balance constraints (debit = credit enforced via DB CHECK). |
| Mero Board | Production | Workspaces, projects, kanban boards, task dependencies, time logging, templates, watchers. 6 pages with deep functionality. | WebSocket performance test for live board updates. Add bulk-action UX for cards. |
| Mero CMS | Production | Pages, posts, media, forms, form submissions feed CRM. 6 pages. Solid CRUD. | SEO sitemap.xml + robots.txt generation. Public site preview before publish. |
| Mero HR | Beta | Employees, departments, attendance, leave, shifts, payroll, recruitment, performance, exit. 17 pages. | Run an actual payroll cycle on a pilot org. Validate payroll → Accounting JE posting. TDS calculation against Nepal IRD rules audit. |
| Mero Khata | Beta | Ledger, bank reconciliation, VAT, invoicing, WhatsApp share. 11 pages, narrow but coherent. | Polish the trader-onboarding flow (this is the lowest-friction entry product). Validate WhatsApp share UX on real devices. |
| Mero Social | Stub | Single dashboard placeholder page. | Either: ship channels + announcements MVP in 3–4 weeks, OR hide from navigation in beta builds. Don’t ship a stub. |
| Tickets | Improvement | Ticket CRUD, comments, attachments. 5 entities. Basic e2e test exists. | SLA timer + escalation workflow. Reporting dashboard. Customer-facing portal (separate from staff view). |
| Chat | Improvement | 1:1, group, admin chat over Socket.IO. 8 entities. File sharing works. | Read receipts and presence. Notification fan-out. Run gateway in a worker process. Mobile push notifications. |
| Admin dashboard | Improvement | Login, basic org list, user list, audit log viewer. | Roughly 20% complete per team’s task list. Operator console for beta MUST be functional: org suspend/resume, password reset, payment investigation, impersonation, feature flags. |
| Mobile (native) | Missing | Web app is responsive (Tailwind breakpoints). | Out of scope for beta. Roadmap item. For beta, ship the responsive web app with explicit messaging. |
| Nepali UI | Missing | English only. | Out of scope for beta. Roadmap item. Plan: i18n scaffolding before beta even if translations are incomplete. |

# 2. Cross-cutting status (security, ops, quality)

## 2.1 Security & multi-tenancy

| Item | Status | Notes |
| --- | --- | --- |
| JWT auth + refresh rotation | Done | 15m access, 7d refresh, sessions tracked, rotation on refresh. |
| MFA (TOTP) | Done | speakeasy-based; backup codes; setup_completed_at timestamp. |
| Bcrypt password hashing | Improvement | Implicit cost of 10. Pin to 12 explicitly via env before beta. |
| organization_id on every entity | Done | Verified across all reviewed entities. |
| App-layer tenancy filter | Done | Every service filters by organizationId via @CurrentOrg. |
| Postgres row-level security | Missing | Defence-in-depth gap. Add policies on every business table before public beta. |
| Multi-tenancy e2e test | Done | Dedicated spec; needs expansion to every new entity. |
| RBAC (packages/roles/permissions) | Done | Four-tier model with seeded defaults. |
| Helmet + CORS + rate limit | Done | Sane defaults at app + Nginx layers. |
| Audit log coverage | Improvement | Table exists; coverage uneven. Define minimum audited actions and enforce. |
| Secret management | Improvement | .env-file based. Move to KMS / Vault before scale. |

## 2.2 Payment integrations

| Gateway | Status | Verified for | Outstanding |
| --- | --- | --- | --- |
| eSewa | Improvement | Outbound HMAC-SHA256, test+prod toggle | Inbound webhook signature verification not explicit. Add and test. |
| Khalti | Done | Inbound + outbound flows | Sandbox-to-prod credential rotation runbook. |
| ConnectIPS | Done | Bank rail flow | Long settlement window — ensure UX sets correct expectations. |
| IME Pay | Done | Wallet flow | Webhook replay-attack test. |
| PayPal | Done | Standard SDK | International FX handling test. |
| Stripe | Done | Subscription billing path | Subscription lifecycle event handling (cancel, refund) e2e. |
| Reconciliation | Improvement | payment_allocations table exists | Automated matching report; manual correction UI in admin. |

## 2.3 Test coverage and CI/CD

| Item | Status | Notes |
| --- | --- | --- |
| E2E test suite (api) | Done | 13 spec files covering auth, tenancy, RBAC, payments, accounting, inventory, payroll. |
| Unit test suite (api) | Improvement | Only ~6 .spec.ts files. Targeted coverage for services missing. |
| Frontend tests | Missing | Effectively zero. Largest single quality gap. |
| GitHub Actions PR pipeline | Done | Lint + test + build + main-branch protection. |
| Type-check gate (tsc --noEmit) | Missing | Add to CI. |
| Bundle-size budget | Missing | Add to CI. |
| Security scanning (npm audit, SAST) | Missing | Add at minimum npm audit + dependabot. |
| Husky pre-commit | Done | migration:validate. Add lint + typecheck. |
| E2E gating in CI | Missing | E2E tests exist but aren’t gated. Wire them into the PR workflow. |

## 2.4 Performance, scaling, observability

| Item | Status | Notes |
| --- | --- | --- |
| Winston structured logging | Done | JSON in prod, file rotation. |
| Sentry error + perf | Done | Optional via DSN. Sampling configurable. |
| Prometheus metrics | Done | /metrics scrape endpoint. |
| Health checks | Done | /api/v1/health via @nestjs/terminus. |
| OpenTelemetry distributed tracing | Missing | Sentry covers errors; OTEL needed once cross-service work begins. |
| DB indexes (composite) | Improvement | Inconsistent. Add (organization_id, created_at) on every list table. |
| Caching | Improvement | Redis available but cache use is light; aggressive caching on hot read paths needed. |
| DB connection pool sizing | Improvement | Min 5 / max 20 — fine for one replica, undersized for horizontal scale. |
| Statement timeout | Missing | Set DB_STATEMENT_TIMEOUT to prevent runaway tenant queries. |
| Backups + PITR | Missing | No scheduled backups in deploy artefacts. Critical gap. |
| Single-instance API | Improvement | Nginx upstream supports more replicas; horizontal scale untested. |

# 3. Beta gate — the eleven things that must be true

If any one of these is false on the day of public beta launch, do not launch. Each item maps to a concrete deliverable below.

| # | Gate | Effort | Definition of done |
| --- | --- | --- | --- |
| 1 | Payment-webhook signature verification on every gateway | 1 wk | Each gateway's webhook handler validates the signature and rejects replays. Unit + e2e tests prove it. |
| 2 | Postgres row-level security policies | 1 wk | USING (organization_id = current_setting(...)) on every business table. Connection-pool sets the session var. e2e regression test for cross-tenant access still passes. |
| 3 | Automated daily Postgres backups + verified restore drill | 0.5 wk | Cron + pg_dump (or managed PITR). Weekly restore-into-side-DB drill. Documented runbook. |
| 4 | System-admin dashboard at ≥80% complete | 2–3 wk | Org suspend/resume, user search + reset, payment investigation, audit log viewer, feature flags, impersonation. Permission-gated. |
| 5 | Tickets module: SLA + escalation + reporting OR removed from beta nav | 1–2 wk | Either ship the missing pieces or ship a feature flag that hides the module. |
| 6 | Chat module: presence + read receipts OR removed from beta nav | 1–2 wk | Same: ship or hide. Don’t ship a half-finished feature. |
| 7 | Mero Social: ship MVP OR hide from beta nav | 0.5–3 wk | MVP = channels + announcements + DMs. If not ready, hide. |
| 8 | Bcrypt cost pinned to 12 via env | 0.5 d | BCRYPT_ROUNDS=12 in .env.example, read in auth.service.ts. |
| 9 | Frontend smoke test coverage on every list + form | 2 wk | Playwright or Cypress suite that asserts a real user can list, create, edit, and delete in every Production / Beta module. |
| 10 | CI gates: tsc --noEmit, npm audit, e2e tests, bundle-size budget | 0.5 wk | Workflow updated. PRs blocked on any of these failing. |
| 11 | Beta agreement + data residency statement signed | 0.5 wk | Customers know data is in <region>, backups exist, support SLA, beta-product caveats. |

Total estimated effort across these eleven items: approximately 9–13 person-weeks. Parallelisable across 2–3 engineers, hence the 6–9 calendar-week estimate at the cover.

# 4. Risk register

Severity uses Impact (if it happens, how bad?) and Likelihood (will it happen during beta if unaddressed?). High / Medium / Low.

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Cross-tenant data leak via missing organization_id WHERE clause | High | Low | App-layer filter is consistent today. Add Postgres RLS as defence-in-depth (Gate #2) to make this nearly impossible. |
| Payment webhook spoofed → fraudulent payment marked completed | High | Med | Sign-and-verify every webhook (Gate #1). Add replay-attack tests. Reconcile against gateway dashboard daily. |
| Database loss with no backup | High | Med | Schedule daily pg_dump + offsite copy + weekly restore drill (Gate #3). Document RPO and RTO in beta agreement. |
| API process saturated by misbehaving WebSocket client | Med | Med | Move Chat gateway to a worker process; cap per-connection CPU; add Sentry transaction monitoring. |
| Frontend regression breaks a core flow under load | High | Med | Playwright/Cypress smoke suite gating every PR (Gate #9). Sentry alerts wired to on-call channel. |
| Customer support cannot do day-to-day ops via UI | Med | High | Build out admin dashboard (Gate #4). Until then, every support action requires engineering, which doesn’t scale. |
| JWT_SECRET leaks via .env file copy | High | Low | Move secrets to a managed store (Vault, AWS Secrets Manager, Doppler) before scale. Document rotation procedure. |
| eSewa changes API contract → silent payment failures | Med | Low | Health-check ping on every gateway. Sentry alert on payment failure-rate spike. Reconciliation report catches this within 24h. |
| Single Postgres instance fails (hardware / disk full) | High | Low | Move to managed Postgres with HA before scale. For beta: monitor disk usage; alert at 70% / 85% / 95%. |
| Bcrypt cost too low → rainbow-table risk if DB leaks | Med | Low | Pin to 12 (Gate #8). Plan a re-hash migration for any users created with cost 10. |
| Frontend bundle too large → slow first-paint on Nepali 3G | Med | Med | Bundle-size budget in CI (Gate #10). Code-split per app (already in place). Monitor lighthouse score. |
| TDS / VAT calculation regression after Nepal tax rule change | High | Med | Snapshot regression tests for every tax-rule branch. Subscribe to IRD updates. Hot-fix release SLA documented. |

# 5. The recommended sequence

A 9-week plan. Front-load security and ops; mid-load admin tooling; back-load test coverage and dogfooding.

## Weeks 1–2 — Hardening

- Pin bcrypt cost (Gate #8) — 0.5 day.

- Payment webhook signature verification across every gateway (Gate #1).

- Postgres row-level security (Gate #2).

- Composite indexes on (organization_id, created_at) for every list-view table.

- DB_STATEMENT_TIMEOUT set; connection pool resized for production.

## Weeks 2–4 — Operations

- Daily Postgres backup with weekly restore drill (Gate #3).

- Sentry alerts wired to on-call channel for error rate, payment failure, queue depth.

- Prometheus dashboards for the four golden signals per service.

- Decision: which of Tickets / Chat / Social ship vs. hide for beta (Gates #5, #6, #7).

## Weeks 3–6 — Admin dashboard build-out

- Gate #4 — every operator action accessible via UI: suspend org, reset password, investigate payment, view audit log, toggle feature flags, impersonate.

- Permission-gated by SystemAdmin role; every action writes to audit_logs.

## Weeks 5–7 — Test coverage

- Frontend Playwright suite covering every list + form (Gate #9).

- Multi-tenancy e2e expanded to cover every entity in beta scope.

- CI gates added: tsc --noEmit, npm audit, e2e tests, bundle-size budget (Gate #10).

- Husky pre-commit extended with lint:check and typecheck.

## Week 7 — Beta agreement, data residency, support runbooks

- Beta agreement signed by every closed-beta participant (Gate #11).

- Public-facing data residency + backup statement on the marketing site.

- Support runbooks for the top 10 expected incidents.

## Weeks 8–9 — Closed beta

- 25 hand-picked design partners across the three target segments (Khata-only, Growth, Business).

- Daily standup on customer feedback; weekly hot-fix release cadence.

- Track: P1 issues, time-to-first-value per customer, payment success rate, multi-tenancy isolation incidents (target: 0).

## Public beta gate review

- All 11 must-do items green.

- Closed beta produced no P0 incidents.

- At least 80% of closed-beta customers issued one real invoice / payroll / payment.

- Public beta agreement and pricing finalised.

# 6. What we are intentionally deferring past beta

Calling these out so they don’t accidentally creep into scope. Each is a roadmap item, not a beta blocker.

- Native mobile app (React Native). Web is responsive; native ships in the next release.

- Full Nepali-language UI. Scaffold i18n now; translate post-beta with paying customers in the loop.

- Workflow / automation builder. CRM has limited automation today; a general builder is post-beta.

- Public API + webhooks for integrators. Internal API is stable; document and open it post-beta.

- Marketplace partner portal for accountants. Multi-org-from-one-login is a future tier.

- Microservice extraction of Chat / Social. Modular monolith holds for beta scale.

- Self-serve billing UI. Beta customers are operator-onboarded. Self-serve checkout is post-beta.

# 7. Final verdict

Mero Jugx is further along than the team probably feels. The platform foundations — auth, tenancy, RBAC, payments, observability — are present and well-implemented. The flagship apps are mature; the beta apps have appropriate self-knowledge in the README; the in-progress apps have working scaffolding.

The path to a public beta is not a re-write, not a rescue — it is a focused 6–9 week sprint on the eleven items in Section 3. Most of them are operational maturity tasks rather than feature work. None requires research or architectural change.

The biggest single recommendation, if only one thing changes: close the loop on operations — backups, signed webhooks, RLS, admin dashboard. The product is good. The product’s ability to recover from incidents at customer scale is what will determine whether the beta succeeds.