# Pre-Beta Work List

Mero Jugx — the inspection checklist before beta release

| Field | Value |
| --- | --- |
| Document | Pre-Beta Work List (v1.1) |
| Scope change | Mero Social and Mero SaaS Kit removed from product (chore/remove-social-saas-kit) |
| Apps in beta scope | 8 — CRM, Inventory, Accounting, Board, CMS (production); HR, Khata (beta-validating); Tickets, Chat (improvement) |
| Total items in this list | 26 — 11 P0, 9 P1, 6 P2 |
| Estimated total effort | ≈12–16 person-weeks (parallelisable to 6–9 calendar weeks across 2–3 engineers) |
| How to use | Walk top-to-bottom. Confirm each item has the named definition-of-done before signing off the beta. |

## Severity legend

P0 — beta blocker. Cannot ship to a paying or referenceable customer until done.

P1 — strongly recommended before beta. Will be discovered by customers if not addressed; expect support pain.

P2 — polish + safety net. Ship without if absolutely necessary, but plan to land in week 1–2 of beta.

## How effort is sized

Effort columns assume one focused engineer, no context-switching. d = days, wk = weeks. “0.5 wk” means roughly 2.5 working days. Where two engineers can work in parallel without stepping on each other, the calendar time is half the listed effort.

# 1. Security and multi-tenancy

| # | Item | Severity | Effort | Owner area | Definition of done |
| --- | --- | --- | --- | --- | --- |
| 1 | Postgres row-level security policies on every business table | P0 | 1 wk | Backend / DB | USING (organization_id = current_setting('app.current_org')::uuid) on every tenant table. Connection pool sets the session var on checkout. e2e regression for cross-tenant access still passes. |
| 2 | Bcrypt cost pinned to 12 via env | P0 | 0.5 d | Backend | BCRYPT_ROUNDS=12 in .env.example, read in auth.service.ts. Plan the re-hash migration for existing users created with cost 10. |
| 3 | Promote tenant context from URL slug to JWT claim | P1 | 0.5 wk | Backend | JWT carries active_org_id; AppAccessGuard validates it matches the slug. Removes the silent default-to-wrong-org failure mode. |
| 4 | Multi-tenancy isolation e2e expanded to every entity in beta scope | P0 | 1 wk | QA / Backend | Tenant A cannot read or mutate any record of Tenant B across CRM, Inventory, Accounting, HR, Khata, Board, CMS, Tickets, Chat. One test per entity; ran in CI. |
| 5 | Audit log coverage on every privileged action | P1 | 1 wk | Backend | Define the minimum set: role/permission changes, payment override, refund, employee terminate, invoice void, journal entry approval. Coverage test asserts each emits an audit_logs row. |
| 6 | Secret management: move .env file to a managed store before scale | P2 | 0.5 wk | DevOps | Doppler / Vault / cloud KMS injecting secrets at deploy time. Rotation runbook documented. JWT_SECRET rotation procedure tested. |

# 2. Payment integrations

| # | Item | Severity | Effort | Owner area | Definition of done |
| --- | --- | --- | --- | --- | --- |
| 7 | Webhook signature verification on every gateway | P0 | 1 wk | Backend / Payments | eSewa, Khalti, ConnectIPS, IME Pay, PayPal, Stripe webhook handlers each validate the gateway signature and reject replays. Unit + e2e tests cover both success and tampering. |
| 8 | Reconciliation report (automated daily) | P1 | 1 wk | Backend / Finance | Job pulls each gateway’s settlement file (or API), matches against payments + payment_allocations, flags mismatches. Output viewable in admin dashboard. |
| 9 | Payment failure-rate alerting | P1 | 1 d | DevOps / Observability | Sentry alert when failure rate per gateway exceeds 2% over a rolling hour. On-call channel notified. |
| 10 | Subscription lifecycle tests for Stripe (cancel, fail, refund, dunning) | P1 | 0.5 wk | Backend / Payments | e2e covering: new sub, sub cancel, payment failure with retry, refund, account downgrade. State of organization_apps reflects sub state at every step. |
| 11 | Refund flow end-to-end across CRM ↔ Accounting | P1 | 0.5 wk | Backend | Refund issued in CRM creates the inverse JE in Accounting; payment_allocations rebalanced; audit log entry. Tested with each gateway that supports refunds. |

# 3. Operations, backups, observability

| # | Item | Severity | Effort | Owner area | Definition of done |
| --- | --- | --- | --- | --- | --- |
| 12 | Automated daily Postgres backups with verified restore drill | P0 | 0.5 wk | DevOps | Cron + pg_dump (or managed PITR). Backup copied off-host. Weekly automated restore-into-side-DB drill. Runbook for emergency restore signed off. |
| 13 | Database statement timeout configured | P0 | 0.5 d | Backend / DB | DB_STATEMENT_TIMEOUT set (e.g. 30s). Verified via tail of pg_stat_statements that no query exceeds. Prevents one tenant’s runaway query starving everyone. |
| 14 | Composite indexes on every list-view table | P0 | 0.5 wk | DB | (organization_id, created_at) on crm_leads, crm_deals, products, stock_movements, journal_entries, customers_sales_invoices, hr_attendance, tasks, tickets, messages, etc. EXPLAIN confirms index usage. |
| 15 | Sentry alerts wired to on-call channel | P1 | 1 d | DevOps | Alerts on: error rate > 0.5%, P95 latency > 600ms, payment failure spike, queue depth, DB connection exhaustion. Test alert fired and acknowledged. |
| 16 | Prometheus dashboards — four golden signals per service | P1 | 0.5 wk | DevOps | Latency, traffic, errors, saturation. Dashboards on a TV in the team room or pinned in the on-call channel. |
| 17 | OpenTelemetry distributed tracing alongside Sentry | P2 | 1 wk | Backend | OTEL spans across HTTP → DB → Redis → webhook for performance work. Sentry continues to handle errors. Traces sampled at 5%. |

# 4. App-level beta gates

| # | Item | Severity | Effort | Owner area | Definition of done |
| --- | --- | --- | --- | --- | --- |
| 18 | Tickets: SLA timer + escalation + reporting (or hide from beta) | P0 | 1–2 wk | Backend + Frontend | Either: SLA fields on tickets entity; background job ages tickets; escalation chain; reporting dashboard with breach metrics. OR: feature flag hides Tickets from nav for beta. Decide and own the choice. |
| 19 | Chat: presence + read receipts + notification fan-out (or hide from beta) | P0 | 1–2 wk | Backend + Frontend | Either: Socket.IO presence (online/away/offline); message_read_status updates on view; notification fans to in-app + email + mobile push. OR: feature flag hides Chat from nav for beta. |
| 20 | Mero HR: real payroll cycle dry-run on a pilot tenant | P0 | 0.5–1 wk | HR module + Finance | End-to-end: attendance → leave → shift assignment → payroll run → TDS calculation against current Nepal IRD rules → JE posting into Accounting → bank file generated. Reconciles to manual calculation within 0 NPR. |
| 21 | Mero Khata: trader-onboarding flow polished + WhatsApp share validated on real devices | P1 | 0.5 wk | Frontend / Khata | First-time customer can sign up, add their first credit ledger entry, and share via WhatsApp in under 3 minutes. Tested on Android 10+ and iOS 15+ with real WhatsApp installed. |
| 22 | Mero Accounting: real fiscal-year close in a sandbox tenant | P1 | 0.5 wk | Accounting | Run year-end close on a populated test org. JEs generated balance to zero. Opening balances roll into the new fiscal year correctly. Audit trail intact. |

# 5. Admin tooling and quality

| # | Item | Severity | Effort | Owner area | Definition of done |
| --- | --- | --- | --- | --- | --- |
| 23 | System admin dashboard ≥ 80% complete | P0 | 2–3 wk | Admin / Backend + Frontend | Operator can: search/suspend/resume any organisation, search users + reset password + force-MFA, view audit log, investigate any payment, toggle feature flags per org, impersonate (with audit). All actions write audit_logs. |
| 24 | Frontend smoke tests for every list + form (Playwright/Cypress) | P0 | 2 wk | QA / Frontend | For every Production / Beta module: smoke suite asserts list loads, create succeeds, edit persists, delete works, validation rejects bad input. Run in CI on every PR. |
| 25 | CI gates: tsc --noEmit, npm audit, e2e tests, bundle-size budget | P0 | 0.5 wk | DevOps | Workflow updated. PRs blocked when any of these fail. Bundle-size budget set (e.g. 500KB initial, per-app chunk under 250KB). |
| 26 | Beta agreement + data residency statement signed by every beta customer | P0 | 0.5 wk | Legal / Founder | Document: data location, backup policy, RPO + RTO numbers, support SLA, beta-product caveats, exit/export commitment. Each closed-beta customer countersigns before access. |

# Summary by priority

| Severity | Items | Subtotal effort |
| --- | --- | --- |
| P0 — blockers | 11 items | ≈9.5–12 person-weeks |
| P1 — strongly recommended | 9 items | ≈4–6 person-weeks |
| P2 — polish | 6 items | ≈2–3 person-weeks |
| Total | 26 items | ≈15.5–21 person-weeks |

## Recommended sequence (9 calendar weeks)

- Weeks 1–2 (Hardening) — items 1, 2, 7, 12, 13, 14

- Weeks 2–4 (Operations) — items 8, 9, 15, 16; decisions on items 18, 19

- Weeks 3–6 (Admin tooling) — item 23

- Weeks 4–6 (App validation) — items 20, 22; close items 18, 19 (or hide them)

- Weeks 5–7 (Test coverage and CI) — items 4, 24, 25

- Week 7 (Legal + readiness) — items 5, 11, 21, 26

- Weeks 8–9 (Closed beta) — 25 design partners; daily standup on feedback; weekly hot-fix release

- Public beta gate review — All P0 green, no P0 incidents in closed beta, ≥80% of partners issued one real invoice/payroll/payment.

## Items intentionally NOT in this list

These were on the original roadmap but are deferred past beta on purpose. Calling them out to stop scope creep:

- Mero Social — removed from product (chore/remove-social-saas-kit). Re-evaluate in v2.

- Mero SaaS Kit — removed from product (chore/remove-social-saas-kit).

- Native mobile app (React Native) — web is responsive; native ships next release.

- Full Nepali-language UI — i18n scaffolding only for beta; translate post-beta.

- Workflow / automation builder — CRM has limited automation today; general builder is post-beta.

- Public API + webhooks for integrators — internal API stable; document and open post-beta.

- Self-serve checkout / billing — beta customers operator-onboarded.